## Assurance timeline
Assurance Argument - Steps to Completion
Tasks to be completed | Dates - 2020 | [5 empty] | Dates 2021
| July | August | September | October | November | December | January | February | March | April | May | June | July | August
Finalize core team | Dates - 2020 July: 2020-07-20
clarify roles of core team, criterion teams, and Leadership | Dates - 2020 August: 2020-08-14
Educate Leadership Team @ process and timeline to complete assurance argument | Dates - 2020 August: 2020-08-24
finalize criterion team members | Dates - 2020 September: 2020-09-04
Kick off meeting for all criterion teams | Dates - 2020 September: week of Sep 7
Educate college community @ process and timeline for assurance argument | Dates - 2020 September: 2020-09-23
Educate board @ process and timeline | Dates - 2020 September: Sept meeting
Criterion 1 narrative draft uploaded to HUB for criterion and core team review | Dates - 2020 September: 2020-09-14
Leadership team brainstorm evidence for criterion 1 | Dates - 2020 September: 2020-09-28
Criterion 1 team uploads changes/ additions to narrative draft in the HUB | Dates - 2020 October: 2020-10-02
Core team finalizes criterion 1 narrative | Dates - 2020 October: 2020-10-16
Criterion 1 and CORE teams finalize evidence documents and store in Smartsheet | Dates - 2020 October: 2020-10-30
Criterion 2 narrative draft uploaded to HUB for criterion and core team review | Dates - 2020 October: 2020-10-02
Leadership team brainstorm evidence for criterion 2 | Dates - 2020 October: 2020-10-26
Criterion 2 team uploads changes/ additions to narrative draft in the HUB | Dates - 2020 October: 2020-10-23
Core team finalizes criterion 2 narrative | Dates - 2020 November: 2020-11-06
Criterion 2 and Core teams finalize evidence documents and store in Smartsheet | Dates - 2020 November: 2020-11-20
Criterion 3 narrative draft uploaded to HUB for criterion and core team review | Dates - 2020 November: 2020-11-02
Leadership team brainstorm evidence for criterion 3 | Dates - 2020 November: 2020-11-23
Criterion 3 team uploads changes/ additions to narrative draft in the HUB | Dates - 2020 November: 2020-11-20
Core team finalizes criterion 3 narrative | Dates - 2020 December: 2020-12-11
Criterion 3 and Core teams finalize evidence documents and store in Smartsheet | Dates 2021 January: 2020-01-04
Criterion 5 narrative draft uploaded to HUB for criterion and core team review | Dates 2021 January: 2020-01-11
Leadership team brainstorm evidence for criterion 5 | Dates 2021 January: 2020-01-25
Criterion 5 team uploads changes/ additions to narrative draft in the HUB | Dates 2021 February: 2020-02-05
Core team finales criterion 5 narrative | Dates 2021 February: 2020-02-19
Criterion 5 and Core teams finalize evidence documents and store in Smartsheet | Dates 2021 March: 2020-03-05
Criterion 4 narrative draft uploaded to HUB for criterion and core team review | Dates 2021 February: 2020-02-01
Leadership team brainstorm evidence for criterion 4 | Dates 2021 February: 2020-02-22
Criterion 4 team uploads changes/ additions to narrative draft in the HUB | Dates 2021 February: 2020-02-22
Core team finalizes criterion 4 narrative | Dates 2021 March: 2020-03-08
Criterion 4 and Core teams finalize evidence documents and store in Smartsheet | Dates 2021 March: 2020-03-26
Assurance Argument narrative finalized | Dates 2021 April: April
Assurance Narrative sent to entire college for review | Dates 2021 May: May
Evidence Documents Finalized | Dates 2021 June: June
Entire document out for review | Dates 2021 July: July
Assurance Argument finalized | Dates 2021 August: August

## college Prep timeline
Begin College Preparation
Board Training
Advisory Committee Trainings
Instructor trainings
all college trainings
Exec/Leadership trainings
External partner trainings (high schools/Cesa/workforce/legislators)